## Slide 1: Project Scheduling and Net Work Diagram
Dr. Raghu Bista

## Slide 2: Project Scheduling
Project Scheduling details project activities to be undertaken and assigns time period to each activity so that the project can be completed on time. It is a major function in project management. It serves as operating guide for the project personnel.
Gantt chart and network diagrams are used to schedule project activities.

## Slide 3: Budgeting Project in Terms of Time
To determine completion date for any project, it is necessary to timetable all the activities that make up the project.

## Slide 4: Why Scheduling?
To show starting and ending time of each activity
To find the expected project duration
To find the critical and non critical activity
To allocate resources
To develop and maintain careful control
To make easy in completing work

## Slide 5: Work Breakdown Structure
Work Breakdown Structure (WBS) is a hierarchical structure to logically sub-divide all the work elements of the project into graphical presentation
A project can be logically sub-divided by project phases, location, tasks, sub-contractors etc.

## Slide 6: Components of Work Breakdown Structure
Structure
Description
Coding
Number of WBS Levels
The level of details
Roll-up

## Slide 7: Uses of WBS
It helps to visualize the scope of project clearly
It helps to develop a complete lists of activities of the project
It helps to estimate budget for the project

## Slide 8: Work Breakdown Structure and Description
House
1.0.0
Civil
1.1.0
Plumbing
1.2.0
Electrical
1.3.0
Foundations
1.1.1
Wall/Roofs
1.1.2
Piping
1.2.1
H/C
Water
1.2.2
Fitting
1.3.2
Wiring
1.3.1

## Slide 9: Work Breakdown Structure and Description
Foundations
1.1.1
Rs 30000
Wall/Roofs
1.1.2
Rs 20000
Piping
1.2.1
Rs 10000
H/C Water
1.2.2
Rs 20000
Fitting
1.3.2
Rs 25000
Wiring
1.3.1
Rs 50000
House
1.0.0
Civil
1.1.0
Plumbing
1.2.0
Electrical
1.3.0

## Slide 10: Gantt Chart
In this type of chart, the time that an activity should take is represented by horizontal line, the length of line being proportional to the duration of the activity. The activity moves from left to right and activities being listed from top to bottom.

## Slide 11: Advantages of Gantt Chart
It is easy to understand
It is easy to construct
It helps to allocate resources
It provides to show the current status of the project

## Slide 12: Limitation of Gantt Chart
Gantt Charts are limited in their ability to show the interdependencies of activities

## Slide 13: Network Techniques
1. Program Evaluation and Review Technique (PERT)
2. Critical Path Method (CPM)
Both methods are developed in late 1950s
CPM uses a deterministic approach which suits a project whose time duration can be accurately predicted. PERT uses a probabilistic approach
Expected time of activity in PERT = a+4m+b
6
Where, a = most optimistic (shortest) time, m = most likely time,
b = pessimistic (longest) time

## Slide 14: Requirements for Constructing Network Diagram
Identification of each activity of the project
Estimation of activity time
Identification of immediate preceding activity of each activity
Identification of activities to be undertaken simultaneously

## Slide 15: An Activity
An activity is any task, job or operation which must be completed to finish the project
Work Breakdown Structure helps to identify activities of a project.

## Slide 16: Estimation of activity time
Once we activities of project, we need to estimate the require to complete each activity. It can be estimated based on past experience, expert’s judgment etc.

## Slide 17: Example of Project Activities
Activities | Expected time (weeks) to complete activities | Immediate preceding activities
A B C D E F G | 5 weeks 2 weeks 3 weeks 4 weeks 4 weeks 3 weeks 5 weeks | None None A B A C,D E

## Slide 18: Methods to Construct Network Diagram
Activity on Arrow
Activity on Node

## Slide 19: Activity on Arrow Method
Each activity is represented by an arrow
Arrow moves from one circle to another and is known as initial event to terminal event. Each event is numbered sequentially
Predecessor Activity: Activity which must be completed before the start of another activity
1
2
Activity
3
Activity

## Slide 20: Dummy Activity
Some times Dummy line is introduced to overcome the problem of completing network diagram to establish preceding relationship among activities. It is represented by dotted line. A dummy activity does not have duration and uses no resources. Its sole purpose is to indicate a technological relationship.

## Slide 21: Construction of Network Diagram
1
2
3
4
5w
5
6
A
B
2w
C
3w
E
4w
D
4w
F
3w
G
5w

## Slide 22: Determination of Critical Paths
To know the duration of the project, we have to find critical path from the network diagram
The critical path is the sequence of activities between a project’s starting and finishing time that takes the longest time to complete projects

## Slide 23: Critical activities in the above diagram
A ….. E ……G = (5+4+5) = 14 weeks
B …… D …… F = (2+4+3) = 9 weeks
A ….. C …… F = (5+3+3) = 11 weeks
A, E and G activities are critical activities

## Slide 24: Non-critical activities in the above diagram
Activities B,C,D and F are non critical activities. These activities can be delayed without delaying completion of the project

## Slide 25: Calculation of Activity Slack Time
Slack time is the maximum time an activity can be delayed without delaying the project completion time
Slack time can be calculated in two ways
- Slack time = LS – ES …………… (i)
- Slack time = LF – EF ……………. (ii)
Where, LS = Late start time
ES = Early start time
LF = Late finishing time
EF = Early Finishing time

## Slide 26: Calculation of earliest finish time
Earliest finish time = earliest start time + expected time to complete the activities (duration of activity)

## Slide 27: Calculation of Late start time
Late start time = Late finish time – expected time of an activity (duration)

## Slide 28: Gantt chart showing critical activities
A
B
C
D
E
F
G
Activities
Weeks
(Activities shown with dotted lines are non critical activities)
1 2 3 4 5 6 7 8 9 10 11 12 13 14

## Slide 29: Project Crashing
Project crashing is the process of reducing the duration of project.

## Slide 30: Reasons for Crashing
To address the urgency of the project
To finish project in scheduled time (For example: The project's progress is behind the schedule. But the project must be completed in given time. So then it needs to crash the remaining activities to be in schedule).
Completing earlier than scheduled time will be some times beneficial for the organization

## Slide 31: Crashing Project : Estimating Crash Cost
The crash time of each activity can be estimated to reduce the completion time of project.
Crash cost is the cost associated with doing the job on crash basis
The formula for calculation of crash cost is: Slope = crash cost –normal cost
normal time – crash time

## Slide 32: Option for accelerating activities
Improve the productivity of the existing resources
Changing the working methods
Increasing project resources which is most common

## Slide 33: Crash Strategy (Process of Crashing)
Identify the activities that needs to be crashed in order to reduce project completion time.
Crash least expensive activity which lies on critical path.
Select also easiest activity to crash

## Slide 34: Preparation of Final Schedule
Based on slack time of each activities, resource constraint and crashing opportunities, final schedule will be prepared.
Sub schedule will also be prepared for each activity

## Slide 35: Why schedule fail ?
Wrong estimation of time
Not selecting proper time
Technical difficulty
Lack of people’s commitment

## Slide 36: Schedule Awareness
The simple way to create schedule awareness is by displaying the progress achievements and target dates at visible place

## Slide 37: Thanks